| # | Steps | Notes & explanations |
| --- | --- | --- |
| 1 | Discuss and identify LIST OF TASKS needed to run one of the activities of your workplan | Task is regarded as a sub-activity, under each workplan's activity (as per prodoc) Example: Activity #1 Task #1 .... Task #3 |
| 2 | Discuss and identify a TIMELINE for the implementation of each task | Use quarters as time units |
| 4 | Based on the total budget allocated for your specific activity (as per prodoc) make a tentative BREAK-DOWN relatively to each combination task/quarter |  |
| 2 | Discuss and identify EXPERTISE/S AND STAFF needed to carry out each task | Put on focus responsibilities of tasks |

EXAMPLE OF PRELIMINARY PLANNING of ONE ACTIVITY of WORKPLAN

| Activity | Budget USD$ | 2012 | 2013 | 2014 | 2015 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Responsibility |
| Activity 8: Facilitate consultative and formalization process for the Suwarrow Island Environment Regulations and Management Plan | 10,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NES, TIS, OPM,CAC |
| Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Community consultation | 2000 |  |  | 1000 |  |  |  |  | 1000 |  |  |  |  |  |  |  | Facilitator |
| Identify and endorse Suwarrow Nat’l park authority | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Natl Coord |
| Review current management plan and write regulations | 6000 |  |  | 3000 |  |  |  |  | 1000 | 2000 |  |  |  |  |  |  | PA expert |
| Education and awareness | 2000 |  |  | 500 |  |  |  |  | 500 | 1000 |  |  |  |  |  |  | Natl Coord with advise from Communication expert |
| Cabinet endorsement of regulation and management plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Natl Coord |
|  | 10000 |  |  | 4500 | 0 | 0 | 0 | 0 | 2500 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 |  |