The National Coordinators refer by email to the GEF Project Assistant (Anna Bertram; annab@sprep.org) for any matter concerning the implementation of the activities of the project and workplan and for reporting issues. Most important and relevant communication should be copied to the national manager and the regional project manager (David Moverley; davidm@sprep.org).

If email communication is not sufficient, then telephone will be used to back up email communication.

A monthly telephone/Skype call will be operated by GEF Facilitator to each national coordinator to monitor progress of implementation, backed up by an update communication using the SPREP IAS Mailing List for national coordinators.

In-country assistance missions are organised when this is deemed necessary, according to availability of travel funds and time. A minimum of two in-country assistance missions are organized and carried out for each country participating in the IAS project (inception workshop and start-up of the project): see table below.

| Country | Inception workshop | Project start-up |
| --- | --- | --- |
| Cook Islands | 26–28 May 2011 | 18-25 March 2013 |
| Federated States of Micronesia | 13 Dec 2011 | 1-8 December 2012 |
| Kiribati | 17-22 August 2012 | 10-16 June 2013 |
| Republic of Marshall Islands | 30 Nov 2011 | 27 November- 1 December 2012 |
| Niue | 10-11 Jan 2011 | 18-22 February 2013 |
| Palau | 6 October 2011 | 9-12 December 2012 |
| Papua New Guinea | 25–26 May 2011 | On plan for May 2013 |
| Samoa | 13 Oct 2010 | 9 April 2013 |
| Tonga | 9 Mar 2011 | 18 October - 1 November 2012; 17-21 June 2013; 19-23 August 2013 |
| Vanuatu | 6 Dec 2010 | 25-29 March 2013 |