2020 ABS Project Activities

| Regional Goal | Regional Goal 2: Pacific People benefit from healthy and resilient island and ocean ecosystems |
| --- | --- |
| Indicator | PICTs strengthened its capacity to implement the Objective 3 of the Convention on Biological Diversity on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits arising from its utilization, thereby contributing to conservation and sustainable use of resources. |
| Outcomes: | Significant Outcome: |
|  | 1.1 | PICTs have common understanding of the shared assets, values and needs on which to base collective policy for use nationally and at convention or regional instrument level |
|  | 1.2 | Future directions of policy development for the region identified |
|  | 2.1 | National Authorities take informed decisions on the ratification of the protocol and future implementation |
|  | 2.2 | Appropriate policies are in place for countries |
|  | 3.1 | An enabling environment is created which will lead to the implementation of the basic provisions of the Nagoya Protocol |
|  | 4.1 | Countries share information and gain from the experiences of other members and the Pacific Community |
|  | 4.2 | Effective management and delivery of projects meeting agreed measurable outputs and indicators |
|  | 4.3 | Improved collaboration with development partners |
|  | Moderate Outcome |
|  | 5.1 | Improved communication with project countries |
|  | 5.2 | Improved collaboration with development partners |
|  | Partial Outcome |
|  | 6.1 | Appropriate policies, laws and regulations are developed for countries |
|  | 6.2 | Effective system in place for communication and dialogue on the potential phase 2 of the regional project |
| Organizational Outcome | RO2.2 | Supported the conservation and sustainable use of marine, coastal, and terrestrial ecosystems and biodiversity, consistent with international commitments |
| Main Objective | Provide advice to the ABS Focal Points of 14 PICTs on technical and legal aspects of the project Regularly monitor emerging ABS implementation initiatives that are relevant to the Pacific region, and provide advise on these to regional and national stakeholders Run regional public awareness and capacity development workshops Prepare drafting instructions, and review draft national ABS laws/regulations/policy proposals Work closely with relevant programmes within and outside of SPREP to support conservation and sustainable use of marine, coastal and terrestrial ecosystems and biodiversity consistent with international commitments. Ensure timely implementation and successful completion of Regional ABS project and activities and consistency with donors and international obligations and SPREP’s strategies, commitments and goals. |
| Programme | Island and Ocean Ecosystem |
| Output description | Regional position is prepared based on systematic analysis of common assets/values and needs between the countries and used to support international negotiations Policy directions for individual countries reflect a common vision for the region National scoping studies of the existing laws related to ABS undertaken to inform the best ABS frameworks for individual countries National ABS laws and policies are drafted and submitted for approval Public awareness workshops are held targeting parliamentarians and decision makers including women’s group and communities alike Enabling environment is created |
| Assumption | Staff with the required skills and experience to effectively coordinate ABS at the country level Relevant stakeholders and political support |

| Activities | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Steering Committee Meeting | 31 Apia (PMU) |  |  |  |  |  |  |  |  |  |  |  |
| Capacity Building & Inter-regional exchange (NGO) workshop (Fiji) |  | 5- 8 Suva (OK) |  |  |  |  |  |  |  |  |  |  |
| Capacity Building IAC consultations (CBD – Post 2020) |  | 24 – 28 Kunming- China (RC) |  |  |  |  |  |  |  |  |  |  |
| Mid-Term Evaluation (UNEP) |  |  | 9-13 Apia (PMU) |  |  |  |  |  |  |  |  |  |
| SPREP STAFF ADVANCE |  |  | 19-20 Apia (PMU) |  |  |  |  |  |  |  |  |  |
| ABS Capacity Building Workshop (regional) & ABS initiative |  |  |  | 15-17 Noumea (TBC) |  |  |  |  |  |  |  |  |
| 10th Nature Conference |  |  |  | 20-24 Noumea (OK/RC) |  |  |  |  |  |  |  |  |
| Country Mission (Cook Islands) |  |  |  |  | 4-8 R’tonga (tbc) |  |  |  |  |  |  |  |
| Pacific ABS Side Event at the World Conservation Congress in Partnership. |  |  |  |  |  | 11-19 Paris (TBC) Rahul |  |  |  |  |  |  |
| Country Mission (Kiribati) |  |  |  |  |  |  | 22-24 Tarawa |  |  |  |  |  |
| Bioprospecting Forum |  |  |  |  |  |  | 27 – 31 Brisbane (PMU) |  |  |  |  |  |
| Pre-COP Regional Workshop |  |  |  |  |  |  |  | 17-21 Apia/Nadi TBC |  |  |  |  |
| North Pacific Sub Regional ABS Workshop (Palau) |  |  |  |  |  |  |  |  | 21-25 Koror (TBC) |  |  |  |
| CBD COP (COP MOP)/ABS |  |  |  |  |  |  |  |  |  | 15-29 Kunming |  |  |
| Regional ABS Workshop |  |  |  |  |  |  |  |  |  |  | TBC |  |

2020 ESTIMATED EXPENDITURE BUDGET

| Activity | UNEP Code | Narration | Amount (USD) |
| --- | --- | --- | --- |
| Salaries staff (LA/CDO/FA) | 1100 | Legal Advisor, ABS Capacity Building Officer and ABS Technical Assistant salary for 12 months as per the Project budget. (166,000; 122,000;41,775) | 329,755 |
| Travel & Daily Subsistence Allowance | 1600 | (refer to breakdown in Table 1.2) This includes costs for Project Staff for all the travel as per the calendar above. | 110,136 |
| Country Allocations (National Workshop) | 3202 | 5000 USD per country X 5 countries (Fiji, Cook Islands, Tonga, Vanuatu and Kiribati) | 25,000 |
| Regional Workshop and Inter Regional Exchange Meeting | 3204 | (refer to breakdown in table 1.3) This includes total costs for all the regional workshops or meetings as per the calendar above. This includes DSA, travel for all non SPREP participants and other costs associated with the logistics. | 87,000 |
| Communications Services | 3202 | Allocation for communication and awareness materials. | 5,000 |
| 20 % Percentage Buffer |  |  | 111,378 |
| TOTAL |  |  | 668,269 |

Table 1.2 Travel and DSA Breakdown of Project Staff

| Item | Qty | Amount |
| --- | --- | --- |
| Fiji Workshop (Feb) – Suva – 2 staff | Travel x 2 staff = 3000 7-day DSA x 2 staff = 2632 | 5632 |
| Tonga – 3 staff | Travel x 3 staff = 6000 7-day DSA x 3 staff = 3633 | 9633 |
| Vanuatu – 3 staff | Travel x 3 staff = 6000 7-day DSA x 2 staff = 5607 | 11,607 |
| New Caledonia – 3 staff | Travel x 3 staff = 7000 14-day DSA x 2 staff = 10,080 | 17080 |
| Cook Islands – 3 staff | Travel x 3 staff = 6000 7-day DSA x 3 staff = 5229 | 11229 |
| Paris – 1 staff | Travel x 1 staff = 6000 7-day DSA x 1 staff = 2030 | 8030 |
| Kiribati- 2 staff | Travel x 2 staff = 3000 7-day DSA x 2 staff = 1500 | 4500 |
| Brisbane – 3 staff | Travel x 3 staff = 6000 7-day DSA x 3 staff = 4053 | 10,053 |
| Palau – 3 staff | Travel x 2 staff = 18,000 9-day DSA x 3 staff = 6372 | 24372 |
| China (CBD COP) – 1 staff | Travel x 2 staff = 5000 14-day DSA x 1 staff = 3,500 | 8500 |
| TOTAL |  | 110,136 |

Table 1.3 for Regional/ Sub Regional Workshops

| Meeting | Travel for Participants | DSA | Meeting Venue | Miscellaneous Costs | Total |
| --- | --- | --- | --- | --- | --- |
| Noumea Workshop | NA | NA | 3,000 | 2,000 | 5,000 |
| IUCN Congress | NA | NA | 5,000 |  | 5,000 |
| Brisbane Forum | NA | NA | 2500 | 2500 | 5,000 |
| North Pacific Sub Regional | 8000 (Palau @500 x 16 pple) 8,000 ( FSM @2000 x 4 pple) 6000 (RMI @2000 x 3pple) | 37000 | 3000 | 2000 | 64,000 |
| PreCOP | NA | NA | 7000 | 1000 | 8000 |
| TOTAL |  |  |  |  | 87,000 |